## SUMMARY
SUMMARY
PROJECT NAME |  | OFFEX LIMITED CORPORATE WEBSITE DEV
START DATE |  | 2025-02-11
DURATION |  | 16 weeks
PROJECT MANAGER |  | Jami Johnson
BUDGET SUMMARY
8100 | Material Procurement (Hardware and Software)
68500 | Personnel Costs (Total Person Effort)
8400 | Installation Charges
15950 | Annual Maintenance Charges
100950 | subtotal
15142.5 | Contingency (15%)
116092.5 | TOTAL PROJECT BUDGET

## MATERIAL PROCURMENT
total material procurement |  | HARDWARE |  | SOFTWARE
| 2500 | dev server | 150 | domain name (3yrs)
8100 | 1200 | testing devices various | 600 | web hosting (annual)
| 800 | networking equiptment | 1200 | content management system
|  |  | 600 | design tools (adobe creative suite)
| 4500 | subtotal hardware | 400 | development tools and frameworks
|  |  | 300 | SSL cert (3yrs)
|  |  | 350 | SEO analysis tools
3600

## PERSONNEL COSTS
Total Personnel Costs | 68500
| subtot | weeks | hours | $/hour
Project Management | 32000 | 16 | 40 | 50
Design Phase
UI/UX Designer | 5400 | 3 | 40 | 45
Content Strategist | 1600 | 2 | 20 | 40
Subtotal Design | 7000
Development Phase
Frontend Dev | 9000 | 5 | 40 | 45
Backend Dev | 10000 | 5 | 40 | 50
DBA | 2200 | 2 | 20 | 55
Subtotal Dev | 21200
Testing Phase
QA Tester | 4800 | 3 | 40 | 40
Security Specialist | 1200 | 1 | 20 | 60
Subtotal Testing | 6000
Implementation Phase
sysadmin | 900 | 1 | 20 | 45
content manager | 1400 | 2 | 20 | 35
Subtot Implementation | 2300

## INSTALLATION
8400 | Total Installation Charges
One-time installation costs
1500 | Server Config
800 | Database Setup
1200 | CMS Installation and Configuration
900 | Content Migration
1100 | Quality Assurance Testing
1400 | Security Implementation
800 | Performance Optimization
700 | Search Engine Optimization

## MAINTENANCE
15950 | Total Annual Maintenance Charges
Routine Maintenance (per year)
1200 | Website Hosting
50 | Domain Name Renewal
100 | SSL Certificate Renewal
600 | CMS Updates and Patches | Hours / month | $ / hour | $ / year (cross-check)
2400 | Bug Fixes and Tech Support | 4 | 50 | 2400
Content Management (per year)
4800 | Regular Content Updates | 10 | 40 | 4800
1800 | SEO Maintenance
1200 | Analytics Monitoring
Security Maintenance
1800 | Security Monitoring and Updates
1200 | Backup and Recovery Services
800 | Penetration Testing (Annual)